## Projects (3)
Project ID | Title | Link | Budget | Beneficiary Category | Indicator | Baseline | Target | Notes | Donors | Gender (% female) | VF or Non-VF | Tag | SEH Taxonomy | RISE Taxonomy | Flagship | Indirect Category | Indirect Taxonomy | Technology | Policy or Regulatory Framework | Policy Population
125245 | Energía y Desarrollo Humano | http://open.undp.org/projects/00125245 | 67499 | Policy or Regulatory Framework | Number of documents/tools produced | 0 | 2 |  | Trac Funds |  | Non-VF | [7 empty] | National
5188 | Asunción Green City | PIMS+ | 7493120 |  | Number of urban passengers that use the low-carbon BRT system considering gender equality, use of time and improvement of security | 0 |  | The BRT was cancelled in 2020 therefore this indicator could not be addressed. The 240000 people were related to the BRT that was planned. This indicator cannot be used as it is, as I mentioned previously, related to the BRT which was was cancelled. However, if talking about beneficiaries of alternative modes of transport, we carried out a Mobility Survey which showed that 29% of the population in the AMA owns a bicycle and that are willing to use the bicycle if infrastructure is provided. With the construction of the lanes with the project, people are more likely to use the bicycle. | GEF |  | VF
[5 empty] | Kilometres of bicycle lanes constructed and maintaine | 1 | 100 | This indicator is measured in km (By 2018 the baseline was 58km in the metropolitan area of Asuncion). To date, a total of 20km of bicycle lanes have been constructed by the project and 11 more will be constructed by July 2023. Beneficiaries consist of approximately 2,500,000 residents of the metropolitan area of Asuncion having access to cycling infrastructure and also capacity building. |  |  | VF

## Projects (2) (hidden)
Project ID | Title | Link | Budget | Beneficiary Category | Indicator | Baseline | Target | Notes | Donors | Gender (% female) | Category | Comment | Tag | SEH Taxonomy | RISE Taxonomy | Impact Tier | Flagship | Indirect Category | Indirect Taxonomy
125245 | Energía y Desarrollo Humano | http://open.undp.org/projects/00125245 | 67499 | Policy or Regulatory Framework | Number of documents/tools produced | 0 | 2 |  | Trac Funds | [5 empty] | Renewable Energy | Tier 3
5188 | Asunción Green City | PIMS+ | 7493120 |  | Number of urban passengers that use the low-carbon BRT system considering gender equality, use of time and improvement of security | 0 |  | The BRT was cancelled in 2020 therefore this indicator could not be addressed. The 240000 people were related to the BRT that was planned. This indicator cannot be used as it is, as I mentioned previously, related to the BRT which was was cancelled. However, if talking about beneficiaries of alternative modes of transport, we carried out a Mobility Survey which showed that 29% of the population in the AMA owns a bicycle and that are willing to use the bicycle if infrastructure is provided. With the construction of the lanes with the project, people are more likely to use the bicycle. | GEF |  |  | Can you please clarify if we can use the 240.000 as number of beneficiaries ? If not what what are the new estimates and activities? We wonder that if the BRT was cancelled, how you implent the rest of the budget ? There was no budget of the project Asuncion Green City destined to the BRT project itself, the latter was a separate project financed by the IADB but there were some indicators related to it introduced to the logic frame of the Asuncion Green City Project. The Asuncion Green City project budget related to the component 2 of mobility (in which this indicator is included), has been almost fully executed with only a % remaining related to the ongoing construction of bicycle lanes. Furthermore, from the project Asuncion Green City a new USD 20 million project has been approved by the NAMA Facility to replace 300 ICE buses for Electric Buses in a 5-year project.
|  |  |  | Other | Kilometres of bicycle lanes constructed and maintaine | 1 | 100 | This indicator is measured in km (By 2018 the baseline was 58km in the metropolitan area of Asuncion). To date, a total of 20km of bicycle lanes have been constructed by the project and 11 more will be constructed by July 2023. Beneficiaries consist of approximately 2,500,000 residents of the metropolitan area of Asuncion having access to cycling infrastructure and also capacity building.

## Projects (hidden)
Project ID | Title | Link | Budget | Beneficiary Category | Indicator | Baseline | Target | Notes | Donors | Comments
125245 | Energía y Desarrollo Humano | http://open.undp.org/projects/00125245 | 67499 |  | Number of documents/tools produced | 0 | 2 |  | Trac Funds
5188 | Asunción Green City | PIMS+ | 7493120 |  | Number of urban passengers that use the low-carbon BRT system considering gender equality, use of time and improvement of security | 0 | 240000 | The BRT was cancelled in 2020 therefore this indicator could not be addressed. | GEF | Can you please clarify if we can use the 240.000 as number of beneficiaries ? If not what what are the new estimates and activities? We wonder that if the BRT was cancelled, how you implent the rest of the budget ? | There was no budget of the project Asuncion Green City destined to the BRT project itself, the latter was a separate project financed by the IADB but there were some indicators related to it introduced to the logic frame of the Asuncion Green City Project. The Asuncion Green City project budget related to the component 2 of mobility (in which this indicator is included), has been almost fully executed with only a % remaining related to the ongoing construction of bicycle lanes. Furthermore, from the project Asuncion Green City a new USD 20 million project has been approved by the NAMA Facility to replace 300 ICE buses for Electric Buses in a 5-year project. | The 240000 people were related to the BRT that was planned. This indicator cannot be used as it is, as I mentioned previously, related to the BRT which was was cancelled. However, if talking about beneficiaries of alternative modes of transport, we carried out a Mobility Survey which showed that 29% of the population in the AMA owns a bicycle and that are willing to use the bicycle if infrastructure is provided. With the construction of the lanes with the project, people are more likely to use the bicycle.
[5 empty] | Kilometres of bicycle lanes constructed and maintaine | 1 | 100 | This indicator is measured in km (By 2018 the baseline was 58km in the metropolitan area of Asuncion). To date, a total of 20km of bicycle lanes have been constructed by the project and 11 more will be constructed by July 2023. Beneficiaries consist of approximately 2,500,000 residents of the metropolitan area of Asuncion having access to cycling infrastructure and also capacity building.

## Beneficiary Categories
Beneficiary Category | Indicator
Electricity Access | Number of people, disaggregated by sex, who gain access to clean electricity (direct access to electricity, lighting, cooling, etc.)
Energy (MW added) | Number of MW installed capacity
Clean Cooking | Number of people who gain access to clean cooking (direct access to clean cook stoves, clean fuels, biomass, etc.).
Clean Heating | Number of people who gain access to clean heating (direct access to clean electric heaters, clean fuels, etc.).
Agriculture and Food System | Number of people who gain access to clean, affordable, and sustainable electricity for agricultural and food system activities (direct access to power machines for crop, processing, milling, grinding, de-husking, pressing, canning, sealing and packaging electricity, heating, cooling, solar water pumping for irrigation etc.)
Health Services | Number of people who gain access to health care facilities (direct access to electricity and heating systems for clinics, hospitals, health centers etc.)
Water Services | Number of people who gain access to water services (powering water pumps, water distributions, waste management, etc.).
Education Services | Number of people who gain access to education services through clean energy systems (including students, teachers, etc.)
Transportation and E-mobility Services | Number of MJ saved from transport and e-mobility interventions (e.g., electric vehicles, charging stations, etc.)
Energy Efficiency Services | Number of MJ saved from energy efficiency interventions (e.g., building efficiency, industries, etc.)
Energy Infrastructure Services | Number of people who benefits from energy infrastructure interventions (streetlight, transmission, and distribution lines, etc.)
Other Energy Services | Access to other service (electric vehicles, industries efficiency etc.)
Financing support | Support for the development of market ecosystem
Medium Enterprises | Support for the development of medium enterprises in the energy transition market
Small Enterprises | Support for the development of small enterprises in the energy transition market
Capacity Building Training | Number of people who benefits from training for enterprises on the energy business and energy finance.
Entrepreneurship Training | Training for enterprises on the energy business is assumed to result in at least 100 direct beneficiaries
Market Intervention | Volume of investment (US dollars) leverage removing barriers to private and public investment in clean, reliable, affordable, and sustainable energy solutions and energy efficiency for social infrastructure, productive use of electricity and other services
Campaign Participant | Individuals who participate in advocacy and campaign on energy
Policy or Regulatory Framework | Number of people supported by policy and regulatory framework development on clean, affordable, and sustainable energy
Other | Any other type of beneficiary (please specify justification in Notes)