Project Title : Local Development Program of the 145 territories (PDL-145T)

Project Number:

Implementing Partner:

Start Date:January 2022 End Date: 			December 2023PAC Meeting Date		:

Brief Description

The Local Development Program dedicated to the 145 territories (PDL-145T) is a government program, adopted at the thirty-fourth meeting of the Council of Ministers held on December 24, 2021, which aims to reduce spatial inequalities and transform the living conditions and environments of Congolese populations living in rural territories hitherto underserved by basic social infrastructure and services. It is backed by pillar 5 of the National Strategic Development Plan (PNSD) 2019-2023 in its "balanced development of the provinces" component. It is part of the Government's ongoing efforts to significantly reduce poverty, combat territorial inequalities and promote development from the 145 territories of the Democratic Republic of Congo (DRC). PDL-145T will be financed from the State Budget's own resources, in order to correct the disparities in sustainable human development between urban and rural areas, reduce poverty and growing inequalities and transform the living conditions of populations by significantly improving the public offer of basic socio-economic services in all rural territories of the DRC. The operational activities of PDL-145T will be implemented under four components: (i) Development of basic socio-economic infrastructure; (ii) Revitalization of local and rural economies; (iii) Strengthening local governance; and (iv) Development of a geo-referenced information system for monitoring PDL-145T and other country programs. The implementation of this Programme is expected to significantly reduce poverty and spatial inequalities, improve rural populations' access to basic socio-economic infrastructure and services, increase the incomes of rural agricultural producers, improve food security, increase the access of young people and women to income-generating activities and better manage the risks to which rural populations are exposed. The programme will also strengthen local governance as well as the capacity for initiatives and resilience of vulnerable communities. UNDP will implement this programme in 9 provinces across 5-4 ruralterritories, based on a cost-sharing agreement to be signed with the Government of the DRC. The remaining provinces (14) will be transferred to other implementing partners at the discretion of the Government. The overall cost of the PDL-145T part entrusted to UNDP is estimated at USD 619,829,499 (USD Six hundred and nineteen million eight hundred and twenty-nine thousand four hundred and ninety-nine), fora total of USD 1.6 6 billion. It will be financed mainly from the resources of the Government of the Democratic Republic of the Congo. The UNDP portion of PDL-145T will put in place expedited arrangements and procedures to complete its activities within the agreed timeframe and with the required quality assurances. UNDP will also work to strengthen resource absorption capacities and ensure effective transfer of expertise to national structures on a sustainable basis.

The PDL-145T is perfectly aligned and in tune with: - The National Strategic Development Plan (PNSD) 2019-2029: pillar 5 on environmental protection, fight against climate change, sustainable and balanced development, component "balanced development of the provinces". - The Government Action Plan (PAG) 2021-2023: - The United Nations Cooperation Framework for Sustainable Development (UNSDCF) 2020-2024. Axis 2 : Inclusive economic growth, agricultural development, capturing the demographic dividend, social protection and sustainable management of natural resources Effect 1. 1: By 2024, the Congolese people enjoy sustainable inclusive economic growth driven by agricultural transformation, economic diversification open to innovation and the promotion of youth and women's entrepreneurship. Axis 3: Access to basic social services and humanitarian assistance Effect 3. 1. Especially the most vulnerable populations benefit from equitable, quality and sustainable access to BSS, including HIV/AIDS - The Country Programme Document (CPD) 2020-2024 of the United Nations Development Programme in the DRC: Priority II : Economic transformation and sustainable management of natural resources Effects: 1.1. & 3.1. of the UNSDCF The expected effects of PDL-145T (with gender marker 2 or 3) are: - Outcome 1: Access to basic socio-economic infrastructure and services for populations in the 145 territories is significantly improved - Outcome 2: Local and rural economies are revived and energized - Outcome 3: Local and community development management capacities are strengthened - Effect 4: An interoperable geo-referenced monitoring information system is developed and made operational The overall impact of the program: - The socio-economic and health living conditions of rural populations are significantly and sustainably improved. Programme anchor institutions: Prime Minister & Ministry of Planning

| Total resources required |  |  |
| --- | --- | --- |
| Total resources allocated |  |  |
|  | UNDP TRAC |  |
|  | DONOR |  |
|  | GOVERNMENT |  |
|  | IN-KIND |  |
| Unfunded |  |  |

Approved by (signatures):

| On behalf of the Government |  |  |
| --- | --- | --- |
| Name and Title SEM Christian MWANDO NSIMBA Minister of State, Minister of Planning | Signature | Date & cachet |
| Name and Title SEM Aimé FIGHTING SANGARA Minister of State, Minister for the Budget | Signature | Date & cachet |
| Name and Title SEM Nicolas KAZADI KADIMA NZUJI Minister of Finance | Signature | Date & cachet |
| On behalf of UNDP |  |  |
| Name and Title M. Dominic SAM Resident Representative | Signature | Date & cachet |
| Read and Approved Name and Title Jean-Michel Sama Lukonde Prime Minister, Head of Government Signature Date and Stamp |  |  |

Table of Contents

I.ANALYSIS OF THE SITUATION IN THE		COUNTRY 6

1.1.Overall country context		6

1.2.Specific context of the territories		9

1.3.Rationale for Program		15

II. 		PROGRAMME STRATEGY 16

2.1.Overall 		and specific objectives of Programme		16

2.2.Program 		Components		17

2.3.Programme 		change theory		18

2.4.Strategic 		approach & operating principles of the programme		.		 21

2.5.Prerequisites for the launch and successful implementation of TDP-145T 25

III. 		RESULTS AND PARTNERSHIPS		26

3.1.Expected 		results of the programme		26

3.2.Partnerships				 30

3.3.Sustainability 		and scaling		31

IV. 		RESOURCES AND RESULTS FRAMEWORK		31

4.1.Resources 		required to achieve expected results		31

4.2.Resources 		and Results Framework		33

MONITORING AND EVALUATION FRAMEWORK FOR PROGRAMME		39

VI. 		INSTITUTIONAL ARRANGEMENTS 		FOR GOVERNANCE AND MANAGEMENT		 OF PROGRAMME		41

6.1.Programme 		management and control arrangements		41

6.2.Programme 		steering and coordination		41

6.3.Strategic 		Steering Committee		42

6.4.Political 		Steering Committee (CPP)		42

6.5.National 		Operational Coordination (CON)		42

6.6.The		 		Provincial and Territorial Monitoring Committee (CPTS)		43

6.7.Program				 Management Unit		44

6.7.1.Procedures 		for recruiting and acquiring goods and services		44

6.7.2.Communication & appropriation		45

VII. 		Cadre Legal		45

VIII. 		Risk Management		46

IX. 		ANNEXES		51

ANNEXES:

- Report on the qualityassurance of the programme;

- Model social and environmental screening;

- Risk analysis;

- Capacity assessment: results of partner capacity assessments ( including HACT micro-assessment);

- ToR of the political and strategic steering committees, as well as the technical monitoring committee

- ToR key management positions in the Programme Management Unit;

- Organization chart of the Program Management Unit;

- Table of resource disbursements by the Congolese government.

# ANALYSIS OF THE SITUATION IN THE COUNTRY

# Overall country context

- The Democratic Republic of Congo (DRC) is a fragile country emerging from a long period of political and humanitarian crises, against a backdrop of violence and armed conflict.  Its area is estimated at 2.345 million square kilometers.   Its population is estimated in 2020 at 98 million. Witha population growth rateof 2.9%, it is expected to double every 25 years.  Women (51%) and young people (60%) make up the largest proportionof the population.

- Since 2006 (with the promulgation of the Constitution of the 4th Republic), the country has made significant progress in the political fields  (organization of three general elections 2006-2011-2018, implementation of territorial decentralization, etc.). )), security (reunification of the country, creation of a new republican army, and c.), economic (anaverage growth of 4  % between 2005 and 2019),  and human development  (30  % increase in the HDI between 1990 and 2019  ). The institutional change that took place after the December 2018 general elections reinforced thistransformational dynamic and gradually restored  the social contract.  Theinternal security situation is improving somewhat, thanks in particular  to the recent establishment of a siegeon the two eastern provinces most affected by armed groups (Ituri & North Kivu) and to transnational military cooperation.

- Over the period 2010-2020, the country recorded an average economic growth of nearly 4%, above the African average (2.6%), supported  by structural reforms and  institutional stability, all of which benefited from the support of development partners, despite an unfavorable context marked by the volatility of commodity prices.  However, these good macroeconomic performanceshave not been sufficient to significantly improve the level of the country's socioeconomic indicators and to stimulate the structural transformation of the economy, which is necessary for the increase in aggregate productivity and the improvement of wages.   Economic growth remaineddependent over the period on a limited number ofbranches, particularly mining andagricultural industries. The first (extractive) being very capital-intensive and not very job creation, and  the second (agricultural) is verymuch dominated by small informal producers with low productivityand undercapitalization.

- Despite theefforts madefor decades by successive governments to support the expansion of a competitive private  sector, the Congolese economy has always remainedpoorly diversified, dominated by the informal sector with low productivity (60% of GDP). The formal productive sector (40% of GDP) comprises only a very limited number of enterprises, estimated at nearly 9,000, with a preponderance of labour-intensive mining companies and  undercapitalized and small SMEs.  The low diversification of sources of growth greatly affects the performance of the Congolese economy, and makes it very vulnerable to external shocks.  This situation highlights the fragility of the DRC and the need for the country's authorities to accelerate institutional, economic and social reforms in order to create thenecessary conditions for sustained and inclusive economic growth.

- In terms of human development, the  country has seen significant progress  of 30% in its human development index between 1990 (HDI 0.369) and 2019 (HDI 0.480), driven by good performance in the health system (life expectancy increased from 49 to 60.7 years over the period) and education (the average duration of schooling of children increased from 2.3 to 6.3 years) . Meanwhile, per capita income fell drastically by 37% over the period; This has helped to maintain the country  in the category of least developed countries (LDCs) and countries with low human development (I DH 0.480 in 2019), despite the  economic performance mentioned above  (HDR 2020).   Thus, thecountry's situation  remains characterized by massive poverty (74.7%, estimated at the threshold of $1.9 per day), with a higher incidence in rural areas (84.9%) than urban areas (62.6%), and large disparities between men (75.6%) and women (71.6%) (EGI-SDG 2020).   On the other hand, thestructurally very high levels ofmultidimensional work (64. 5%) and the extrememultidimensional work (36.8%) and the deep economic, social and territorial inequalities (Gini = 0.42; Palma ratio = 2.1; quintile ratio = 8.0) that characterize the  DRC are the result of, among other things, an inequitable redistribution of growth gains, an inefficient social protection system. , and a poorly diversified economy with few job opportunities for the population.

Figure 01: Poverty mapping in DRC

- Population access rates to basic socio-economic infrastructure remain among the lowest in sub-Saharan Africa. Indeed, only 16% of the population has access to electricity, with strong disparities between rural (1%) and urban (35%). As for drinking water, only 26% of the population has access to it, with high accessibility in cities (38%) compared to rural areas (14%). And only 17% of the population has basic sanitation services and 20% improved toilets.  As for the road network, it covers nearly 152,000 Kms, but only 3. 000 Kms are asphalted and in good condition of practicability. Moreover, the spatial density of roads is only 25 km to 1. 000 km² against an average of 204 km in Africa. Road coverage is only 0.9 Km to 1. 000 inhabitants against 3.4 Km for 1. 000 inhabitants in Africa (Office des Routes). The Logistics Performance Index, which ranks countries in terms of the quality of their transport infrastructure, remains very low (the country is ranked 156th out of 160). Thus, most of the territory remains inaccessible by road. Only five (5) provincial capitals would be connected by road to Kinshasa. The rural roads (about 87,000 kms) opening up agro-pastoral production basins are almost impassable.

- Positive developments have been noted in the area of health, but the overall performance  of the national health system remains weak.  Indeed, the country has recorded some successes on the maternal  , child and immunization health front,  including a significant decrease  in maternal  and infant mortality, and an improvement in immunization coverage (see HDR 2020);   However, the population still  faces problems of quality and accessibility to health care, especially in rural areas.  Thus, the overall performance of the national health system remains marked by multiple fragilities and challenges, in particular, (i) a precarious organization of health services, for an insufficient supply of structures and human capacities and  unevenly distributed on the national territory, (ii) a budget largely insufficient to meet - in quantity and quality - the needs of the populations,  (iii) the persistence of recurrent epidemiological challenges (Ebola, measles, malaria) that are amplified, particularly during natural disasters (floods, drought) and pandemics on a global scale such as COVID-19.

- Significant investments have  been made by the government in  the education sector over the  past  three years  (an average of 15% of the budget has been allocated to the education sector over the last 3 years) to develop access, equity and retention and improve the quality of teaching and governance of the sector.  Thanks to these investments, which have made it possible to materialize  the policy of free  education in primary education and the program for the construction of school infrastructure, the net enrolment rates (in primary (87%)  & secondary (45%)), literacy (83%)  and completion in primary (  69%) , as well as the gender parity index  in primary education (95%), have grown steadily over the last three years (see 2020 report of the Ministry of Primary, Secondary and Technical Education).  However, the completion rate in secondary education continues to stagnate at less than 50%, gender disparities widen as the number of years of schooling increases, and inequalities between urban (NER  87.5%) and rural (NER 81%) areas continue to widen.

- Employment continues to be one of the  major concerns, as it lacks the quantity and quality of employment to integrate all those seeking work and generate decent incomes, opportunities for personal development and social integration. The structure of employment in the DRC is marked by the importance of agricultural (68.7% HDR 2019) and informal (88%) jobs, characterized by difficult working conditions (low wages, job instability, lack of social protection and  health and safety measures), which contribute little to the training of the population. u GDP of the country and make growth non-inclusive. Youth employment is also a major challenge in a context characterised by the weakness of the economic fabric and the inadequacy of training for employment, where only 20% of young people reach higher education level, 65.2% are underqualified, and only 2.5% are entrepreneurs, while 500. 000 young graduates  enter the labour market every year.

- Food and nutrition insecurity remains high, particularly in rural  areas, particularly  in conflict-affected areas such as the eastern provinces, and landlocked provinces such as Sankuru. Its main causes are due to  the low volume of investment in agriculture and  basic  infrastructure in the rural world, the persistence of the use of traditional production techniques with  low agricultural yields, and the impacts of weather hazards and climate change. In doing so, the DRC remains among the countries most affected by chronic malnutrition (42.7% in 2018). The prevalence of malnutrition refers to the effectiveness of several systems such as health, agriculture, water and social protection in addressing its root causes.

- Despite the notable efforts made by successive governments over the past two decades to guarantee gender equality, by enshrining it in the February 2006 constitution as revised and amended in 2011, deep gender inequalities persist, affecting all sectors and all private, social, economic and public spheres.  Indeed, only 12.0% of parliamentary seats are held by women in the DRC, and only 36.7% of adult women have attained secondary education, compared to 65.8% ofmen.  The adolescent birth rate is 124.2 births for1,000 women aged 15 to 19 and the female activity rate is only 60.8%, compared with a male activity rate of 66.3%.  Thus, women and girls continue to suffer injustices, sexist attitudes and violence in many forms, in particular gender-based violence (GBV), sexual abuse and exploitation, child marriage and other traditional forms of early initiation of sexuality with adverse effects on their reproductive health, education,  their level of empowerment and the ability of families to invest in their children's human capital. Beyond a legal framework strengthened in recent years, its application, the creation of more opportunities for access to resources and economic opportunities, as well as the prioritization of gender issues at the national level and the institutional framework of reference continue to be lacking.

# Specific context of the territories

The specific context of development of rural territories remains globally marked by:

- A high level of poverty – combined  with high socio-economic inequalities

- Although income poverty(estimated at the $1.9 per day line) fell by nearly 10 points between 2005 (84.5%) and 2020 (74.7%), it remains largely concentrated in rural areas where nearly 70% of the Congolese population lives. According to the latest Sustainable  Development GoalsCluster Survey 2020 (EGI-SDGs), the incidence of poverty stands at 84.9% in rural areas compared to 62.6% in urban areas, a gap of 22 percentage points. The rates of

Depth and severity of poverty would also be 2 to 3 times higher in rural areas (0.425 and 0.255) than urban (0.290 and 0.051) (EGI-SDG, 2020).  This high level of poverty represents a major development challenge to be addressed by energetic pro-poor policies in favour of rural areas.

- Only 2.4% of the rural population has some form of social insurance and about 7.5% a formal social protection system, while in cities, 8.9% and 13.5% of the population respectively are covered by social insurance and a social protection floor. The average consumption expenditure of rural households is two to three times lower than that of urban households (INS 2019). These high inequalities in access to social protection and insurance combined with poverty severely affect the resilience of rural communities.  Reducing the exposureof rural populations to poverty isbecoming a top priority for the government.

- In terms of human development, strong disparities persist in the spatial distribution of human development gains across the national territory. Indeed, only six (6) provinces out of twenty-six (26)have a Human Development Index (HDI) higher than the national average (0.465) (see RNDH 2017). These are Kinshasa (0.606), Kongo Central (0.510), Haut-Katanga (0.506), North Kivu (0.489), Kwilu (0.476) and Tshopo (0.474). The five least born  provinces are Sankuru (0.342), Sud-Ubangi (0.344), Tanganyika (0.356), Mongala (0.375) and Lualaba (0.376).

This inequitable distribution of HDI gains across the country reflects a high level of inequality in the country.

- The rural population also continues to face serious difficulties in accessing bank financing and  factors of production because of their high costs, and benefit little from productive investment from the private sector. This does not allow them to undertake income-generating productive activities.

- Limited access to basic socio-economic infrastructure that increases vulnerability in rural areas

- Access to basic social services (eau, electricity, education, health) is very unfavourable to rural populations.  Despite substantial investment in rural water and electrification services, as  well as the recent creation of a rural education agency to support the government's efforts in this area, people living in rural areas are at a very disadvantage in terms of access to electricity (1%) compared to those living in cities (35%) and Kinshasa (59, 5%). Similarly, only 14% of the population living in rural areas has access to drinking water, compared to 38% in cities and 85% in Kinshasa (RNDH 2017).

| Figure 2: Rural-Urban Electricity Access Rate | Figure 3: Rural-urban drinking water access rate |
| --- | --- |

- Access to education in rural areas remains limited, despite the efforts made. The net enrolment rate in primary education is 72% in rural areas compared with 87% in cities.   The literacy  ratefor 15-24  year olds is 51.4% in rural areas and89.2% in cities. As for functional skills in elementary numeracy, it amounts to only 61.7% in rural areas against 91.0% in cities (EGI-SDG 2020).

- In the field of health, despite the progress made in recentyears, the overall performance of  the country's health care provision, as measured by the index of availability and operational capacity of health services (SARA, DRC) is very low throughout the country, with strong disparities between provinces.  and by place of residence, urban or rural as shown in the tables below:

|  | Averagescore improvedcomfort essential | Average Essential Equipment Score | Average score standard precaution | Average diagnostic ability score | Averageessential medical score | General Service Operational Capacity Index |
| --- | --- | --- | --- | --- | --- | --- |
| Urban | 48 | 87 | 69 | 45 | 23 | 62 |
| Rural | 22 | 72 | 55 | 22 | 20 | 18 |
| RDC | 27 | 75 | 58 | 27 | 20 | 27 |

- In terms of infrastructure, rural areas remain poorly endowed with social and economic infrastructure.  Most rural areas lack passable rural roads, functional hydraulic structures, functioning sewerage systems, and functioning electricity and water supply networks.  As far as rural roads are concerned,  the country has nearly 87,300  km of agricultural feeder roads. This local road network is characterized by a very advanced state of disrepair and plunges the 145 territories into a situation of quasi-isolation on the scale of all the provinces of the DRC. About 70% of agricultural feeder roads to be used in particular to boost the production and evacuation of agricultural products between territories  (places of production) and  cities (places of consumption) are in very poor condition, compared with about 30% in good condition on average.

- As for the housing situation, it remains very worrying in rural areas. Only 7.2  per cent of housing in rural areas  compared to 52.7 per cent in urban areas  is built of sustainable materials. Despite the progress made as a result of the various programmes undertaken (sanitation programme financed by the European Union, village and school sanitation project, etc.), 75% of households still do not have access to sanitation systems, including sewerage, septic tanks and covered latrines. This figure rises to more than 95% in rural areas with virtually no sanitation and sustainable housing system.

- Low agricultural productivity, which keeps the rural population food insecure

- In  terms of agriculture, people in rural  areas are faced with structural food insecurity and low value for their agricultural, fisheries and livestock resources.  The DRC is  indeed endowed with immense agricultural potential: 80 million hectares of arable land, 5 million hectares of pasture, and an important fish reserve. However, the country is almostrecurrent to the prevalence of sometimes acute food crises (24 million people are food insecure and 4.2 million children are affected by chronic malnutrition) (FAO, 2019).

- Food vulnerability results from a combination of factors such as agricultural productivity, access to seeds and other inputs, access to modern production techniques (production and processing equipment), access to markets and sometimes sustainable peace. It also results from the difficulties of the populations to access production facilities because of theirhigh costs and traditional production models with low yields compared to the average of the African zone. The increase in production observed in certain agricultural sectors is mainly due to the increase in areas sown to the detriment of forests, rather than to an improvement in productivity.

- At the same time, the marketing of products from rural agricultural sectors is subject to enormous constraints, the main ones being: (i) the non-existence of storage capacities; (ii) administrative and police harassment and the multiplicity of taxes; (iii) the deterioration of the road network leading to an increase in transport costs; (iv) the low level of investment by the State and private actors; and (v) the virtual absence of adequate mechanisms for financing production activities in rural areas.

- In this context, the development of agricultural value chains in rural areas should make it possible to increase agricultural productivity and, consequently, farmers' incomes while increasing the country's food security.

- In addition, it is worth highlighting  the various systemic risks that jeopardize the development gains of certain territories. It is mainly  the recurrent resurgence of armed conflicts and local, land and even communal conflicts threatening the peace and security of the country in general, and the territories in particular, subsequently leading to  a humanitarian crisis that affected  more than 13.1 million people, including 7.7 million children and 4.3 million internally displaced persons. , in 2019.

- The country is also exposed to various health risks with resurgence and recurrent viral outbreaks (Ebola, Marburg virus, Cholera, Measles, Yellow Fever, etc.) that sometimes affect some provinces and territories. From March 2020, all provinces were gradually affected by the COVID-19 pandemic.

- The DRC also faces various recurring environmental risks. Indeed, the effects of climate change and  natural disasters affect poorer territories that lack systems for prevention  , management and mitigation of climate risks more. The Notre Dame Global Adaptation Initiative Index (ND-GAIN) is valued at 29.5% in 2016 and ranks the country 177th out of 181 countries, the fifth most vulnerable country to climate change.

- The most common types of disasters in the DRC are erosion, floods, heavy rains, collapsesand landslides often resulting in the movement of rural populations, loss of arable land and destruction of basic socio-economic infrastructure.

- Ineffective local governance, hampered by lack of human and institutional capacity and financial resources

- The capacities of the provinces and territories of the DRC to provide basic sovereign and collective services, or even simply to formulate, plan, pilot and implement public policies, have been seriously affected by a long period of political instability and recurrent armed and intercommunal conflicts. This lack of local and provincial management capacities (technical, organizational, institutional, and community) seriously hampers  the formulation and effective implementation of  policy documents and development strategies (local and provincial plans), thus seriously jeopardizing their medium- and long-term development prospects, as well as the achievement of the SDGs.

- Moreover, despite the implementation of the decentralization reform, which is supposed to promote political and economic governance at the provincial and local levels and ensure economic and social development at the grassroots level, capacity and resource deficits prevent remote rural provinces and territories from providing quality public services to their populations. and to address structural development challenges. These deficits highlight the need to provide provinces and territories with timely support to strengthen their human and institutional capacities for the effective implementation of their public policy and the management and maintenance of economic and social infrastructure.

# Program Rationale

- The analysis of the context of development of rural territories indicates that rural areas still face various types of structural challenges, such as the lack of access to basic socio-economic infrastructure, the lack of economic opportunities, not to mention the significant gap accumulated in local development management capacities, which keep them in the poverty trap and lagging behind urban areas. . The combination of these challenges has a negative impact on sustainable human development inrural areas.  In this  context, this backwardness in the development of rural areas becomes necessary in order to give lasting impetus to the country's socio-economic inclusion and social stability.

- With this in  mind, in order to correct the deflections of  pro-poor strategies and policies that have been underway for nearly two decades – which have only marginally affected the rural world –  the Congolese government has decided to develop the programme for the local development of the 145 territories (PDL-145T), a proactive programme  involving massive and varied public investment,  oriented towards the rural world, with the support of itsdevelopment partners.   PDL-145T aims to overcome poverty andterritorial inequalities.  It is backed by the National Strategic Development Plan (PNSD) 2019-2023 through its pillar 5 (balanced development component), the Government Action Program (PAG) 2021-2023 and the  Accelerated Presidential Program to Fight Poverty and Inequalities (PPA-LCPI), and constitutes the central framework ofgovernment action  over the period 2021-2023.

- Thisprogramme is mainly justified by the magnitude of the challenges of multidimensional poverty, social inequalities and vulnerabilities, as well as the systemic risks faced by rural areas. It is a programmatic response to a multidimensional and urgent social demand  of the Congolese population, especially those living in rural areas ofthe country's 26 provinces. In  the  short and medium term,  it will contribute to supporting the endogenous local development of rural areas and  to ensuring the convergence of incomes between rural and urban populations. It does not replace the government program, but is an accelerator of it.

- The COVID-19 crisis that affected the DRC in March 2020 and whose effects have been very devastating for the rural world, still gives meaning to this program dedicated to rural territories.  Indeed, thisCOVID-19 shock further confirms the  urgency for  the Congolese  Government to adjust its public policies  and strategies towards interventions with strong economic and social resonance, particularly in favor of the rural world where the majority of the most vulnerable populations are located, but also the most active such as  young people. This will: (i) revive the country's economy from local growth poles; (ii) reduce the dependence on imports of intermediate goods, basic foodstuffs, by supporting the domestic production of everyday consumer goods to guarantee its food sovereignty; (iii) strengthen resilience to exogenous shocks and diversify sources of growth; (iv) strengthen the economic empowerment of communities and the development of resilient infrastructure.

- In order to implement this ambitious Programme with allthe speed and effectiveness required, the Government of the DRC has requested, among other implementing agencies, the support of UNDP, to take advantage of its comparative advantage, acquired through the experience accumulated in this area, as well as through its strategic programmatic presence in a number of provinces distributed variously throughout the national territory.

# PROGRAM STRATEGY

- Poverty reduction and balanced development of the national territory are among the main priorities of the 2019-2023 national strategic development plan and the government's 2021-2023 action plan based on it. The PDL-145T is one of the Congolese government's preferred instruments for achieving this strategic objective for the period 2021-2023. It will be financed from the state budget. UNDP will implement it in 54 territories in 9 provinces, on the basis of a cost-sharing agreement signed with the Congolese government,  in coherence and in line with other similar programmes carried out within the framework of regular sectoral policies. The remaining provinces and territories will be transferred to other delivery partners at the discretion of the government. The program's interventions will contribute to the significant improvement of the living conditions of the populations living in the targeted rural territories.

# Overall and specific objectives of the programme

- The overall objective of PDL-145T is to correct the disparities in sustainable human development between urban and rural areas and to transform the living conditions of populations by significantly improving the offer of basic socio-economic services in all rural territories of the DRC.

- Specifically, it will involve:

- Improve rural populations' access to basic socio-economic infrastructure and services;

- Promote the development of local and rural economies, in particular through the promotion of rural entrepreneurship, the strengthening of agricultural productivity, the enhancement of agricultural production and the improvement of rural entrepreneurs' access to financial services;

- Strengthen local development management capacities;

- Develop and implement a geo-referenced monitoring and evaluation system;

# Components of the programme

- The PDL-145T is structured around the following 4 components:

- Component 1.  Improve access to basic socio-economic infrastructure and services for people in rural areas

This component aims to establish basic socio-economic infrastructure to contribute to improving the living conditions of populations in rural areas. Its activities areaimed atincreasing the public offer to address the needs of populations in electricity, drinking water, rural service roads, sustainable housing and school and primary health infrastructure.

They will also cover the construction or rehabilitation of public administrative buildings, housing of territorial administrators; and the construction of public markets and living spaces.

- Component 2.  Promoting the development of revived and dynamic rural and local economies

This component will focus more on supporting the development of production and service activities in rural areas.

Its concrete activities will aim to:

  - Support the development of agricultural, livestock and fisheries valuechains in rural areas;

  - Encourage rural entrepreneurship through the creation of small and medium-sized enterprises in rural areas and facilitate access to credit;

  - Improve farmers' productivity by providing inputs, seeds, and agricultural tools and equipment;

  - Promote the creation and implementation of producers' cooperatives and trades with a particular  focus on the inclusion of women and youth;

  - Encourage and support the search for innovative solutions that can lead to the creation of companies / Start-ups by young actors at the level of local communities;

- Component 3. Strengthening local development management capacities

This component aims to develop technical, organizational, institutional and community capacities for local development management for the provision of quality services in rural areas, building on the achievements of the decentralization process.

The capacities to be strengthened are related, on the one hand, to the mastery of the work of realization of basic socio-economic infrastructures and, on the other hand, to the mastery of cultivation techniques, development planning, administrative and financial management, etc.

- Component 4. Develop a geo-referenced monitoring information system capable of providing information on the progress of the programme

The main objective of this component is to establish an effective mechanism for monitoring and evaluating progress in the implementation of the programme.

Ultimately, this system will be made available to the government to serve as an instrument for monitoring the implementation of public policies and programs on the one hand and as a tool to support decision-makingon the other. Effective use of this tool should contribute to a better rationalization of public spending related to infrastructure and equipment and can be integrated into a more comprehensive information and monitoring and evaluation system of the implementation of public investments and serve as a one-stop shop for access to government information and data for several key sectors of the economy and all partners. This tool will also be a contribution of the program to the establishment/development of the Geospatial Data Infrastructure [SDI] of the DRC.

- The first two components of PDL-145T will be implemented by the three implementing agencies chosen by the State, including UNDP. However, the last two components will be implemented exclusively by UNDP.

Cross-cutting activities

- A transversal component taking into account the dimensions of gender, environment and fundamental human rights will be integrated into this programme. Concretely, a comprehensive environmental assessment to identify potential negative environmental impacts will be made andappropriate mitigation measures undertaken. The gender dimension will also be taken into account throughout the programme cycle to ensure that interventions benefit men and women equitably with a particular focus on young people. A set of standards and objectives relating to these three cross-cutting dimensions will be developed and concretized through the implementation of the program.

# program change theory (ToC)

- The analysis of the development context of the DRC reveals that the lack of access to basic socio-economic services and infrastructure, the lack of dynamism of local and rural economies, as well as the weak capacities to manage local development characterize rural and peri-urban areas in the DRC. These socio-economic characteristics, which are still unmet needs in terms  of sustainable human development, are sources of multidimensional poverty among rural populations and, worse, of intergenerational transmission of extreme poverty.

- With this observation and its inevitable consequences, PDL-145T,  given its interventions to affect most key sectors of socio-economic development, aims to irreversibly lay the pillars for a structural transformation of the economies and social institutions of the 145 territories of the DRC, a guarantee of economic progress and sustainable human development.  The implicit hypothesis of paramount importance that the present logic of change will make it possible to verify is that in the long term,  eradicate extreme poverty in all its forms and then, break the queue of the intergenerational transmission of poverty and boost a dynamic of economic growth and sustainable and inclusive human development carried by the 145 Territories of the DRC,  are within reach, and this, under the impetus of massive and proactive public intervention.

- With this in mind, the change in this Programme to Support the  Implementation of PDL-145T  assumes that carefully targeted interventions in rural areas are aimed at "improving rural populations' access tobasic socio-economic  services and infrastructure and  promoting rural and local economies through the development of  rural entrepreneurship and agricultural and  forestry value chains", will allow, thanks to their positive effects, to reverse  in the short, medium and long term, the cycle ofmultidimensional poverty and inequalities as well as   and will trigger a virtuous cycle of resilience, accumulation of human capital and wealth, national solidarity and social cohesion of the country.

- Similarly, "the strengthening of the CAPhascited rural and local development actors, as well as a better development of human capital" have been identified as accelerators ofsocio-economic transformation which will be driven by PDL-145T. Inclusive finance, partnerships between provincial government services  and private operators, the creation of incubators and agro-sylvo-pastoral value chains, as well as the promotion of national citizenship are  also driving factors for the change brought about by this Programme.

- To achieve these transformations, the support program for PDL-145T will prioritize the following main levers: Development and rehabilitation of basic socio-economic infrastructure; Capacity building of state and non-state stakeholders; Promotion of local and rural economies. The overall impact expected in 2023  of the implementation of this Program is  the significant reduction in the prevalence of poverty and inequalities in rural and peri-urban areas of the DRC.

- The targeting for the implementation of the PDL-145T support programme  will focus mainly on extremely poor, vulnerable populations exposed to endemic and  environmental security risks. The priority areas of intervention of the Programme are  the 54 rural territories  belonging to the 9 provinces. The Program's results and resources framework will explain the expected results and the amount of investment required to implement it.

Policy response

Promotionof local economies and agricultural value chains

Local capacity-building

Access to basic socio-economic infrastructure

Construction or rehabilitation:

- Agricultural feeder roads

- School and health infrastructure

- Electrification

- Hydraulic structures (drilling and resource development)

- Administrative buildings and housing of the management staff of the territory

- Energy infrastructure

- Rural entrepreneurship

- Generation of agricultural business incubators

- Support for equipment, agricultural inputs and seeds to producers

- Development of agricultural perimeters

- Strengthening the project management and local work capacities of actors and operators at the provincial and territorial level

- Strengthening technical capacities throughout the value chain of the different sectors

Programmatic response

Operational response

Improving access to basic services, infrastructure and local administrative services

Strengthened development management capacity at national, provincial and territorial levels

Increased rural incomes and improved food security

Results

GOOD

GOVERNANCE

Convergence of incomes and living conditions between urban  and urban environments

Persistent territorial inequalities and multidimensional poverty in rural areas

Implementation of the DSNP, Pillar 5, BalancedProvincial Development  component

Policy response

Promotionof local economies and agricultural value chains

Local capacity-building

Access to basic socio-economic infrastructure

Construction or rehabilitation:

- Agricultural feeder roads

- School and health infrastructure

- Electrification

- Hydraulic structures (drilling and resource development)

- Administrative buildings and housing of the management staff of the territory

- Energy infrastructure

- Rural entrepreneurship

- Generation of agricultural business incubators

- Support for equipment, agricultural inputs and seeds to producers

- Development of agricultural perimeters

- Strengthening the project management and local work capacities of actors and operators at the provincial and territorial level

- Strengthening technical capacities throughout the value chain of the different sectors

Programmatic response

Operational response

Improving access to basic services, infrastructure and local administrative services

Strengthened development management capacity at national, provincial and territorial levels

Increased rural incomes and improved food security

Results

GOOD

GOVERNANCE

Convergence of incomes and living conditions between urban  and urban environments

Persistent territorial inequalities and multidimensional poverty in rural areas

Implementation of the DSNP, Pillar 5, BalancedProvincial Development  component

Local Development Program dedicated to the 145 Rural Territories

Local Development Program dedicated to the 145 Rural Territories

# Astrategic approach & operative aspects of the programme

- The  implementation strategy for the LDP-145T Support Programme is based on the theory of change outlined above and a number of operating principles.

- To achieve the transformational results reflected in the ToC of the Programme, the Strategy of the Programmewill be structured around the following levers and operating principles:

- Accelerated implementation procedures.  UNDP will make use of its effective, rapid, simplified, expendable and practical special procedures  (F ast-Track) in an emergency context with a view to reducing contractual and execution times, while guaranteeing quality and transparency, in particular through regular and systematic monitoring of the United Nations.   of quality and overall security of the program.  In this context, asimultaneous approach to  the implementation of activities will be initiated, coupled with the above-mentioned emergency procurement and payment  procedures to implementing  partners.

- Integrated program product offering  (cluster approach).  It will consist of bringing together and developing several basic social services (rural life, energy, health care, education) on the same platform (or around the same cluster). This will allow an entire community to access several essential basic social services in one place. This makes it possible to produce accelerating effects in terms of improving access to basic social services. The outputs of component 1 are particularly relevant to this type of multisectoral and integrated socio-economic service delivery.

- Territorial approach to implementation.  Given the size of the  Congolese territory, PDL-145T will be subdivided into three geographical areas entrusted to three implementing agencies including UNDP. In view of the logistical challenges associated with the deployment  of the PDL-145T on  a territorial territory,  UNDP will rely on its strategic positioning on the national territory through its field offices as well as on its similar programmes already deployed, to strengthen the effectiveness of its interventions in its areas of intervention.  To do this, the choice of its intervention areas below was dictated by criteria of efficiencyand comparative advantage.

Table 1: UNDP focus areas under PDL-145T

| # | Provinces | Nbrs Territories / Provinces | Territory | Capital |
| --- | --- | --- | --- | --- |
| 1 | Bas-Uélé | 6 | Aketi |  |
|  |  |  | Ango |  |
|  |  |  | Bambesa |  |
|  |  |  | Bondo |  |
|  |  |  | Blind |  |
|  |  |  | Haven't |  |
| 2 | Kasai | 5 | Dekese | Dekese |
|  |  |  | Ilebo | Ilebo |
|  |  |  | Luebo | Luebo |
|  |  |  | Flash | Flash |
|  |  |  | Tshikapa | Kamonia |
| 6 | Maniema | 7 | Kabambare | Kabambare |
|  |  |  | Bare | Bare |
|  |  |  | Kasongo | Kasongo |
|  |  |  | Kibombo | Kibombo |
|  |  |  | Lubutu | Lubutu |
|  |  |  | Pangi | Pangi |
|  |  |  | Punia | Punia |
| 7 | Mongala | 3 | Lisala |  |
|  |  |  | Buba |  |
|  |  |  | Bongandanga |  |
| 7 | Sankuru | 6 | Katako-Cup | Katako-Cup |
|  |  |  | Bike | Bike |
|  |  |  | Lodja | Lodja |
|  |  |  | Lomela | Lomela |
|  |  |  | Lubefu | Lubefu |
|  |  |  | Lusambo | Lusambo |
| 8 | South Kivu | 8 | rifle | rifle |
|  |  |  | Idjwi | Idjwi |
|  |  |  | Cabaret | Cabaret |
|  |  |  | Kalehe | Kalehe |
|  |  |  | Mwenga | Mwenga |
|  |  |  | Shabunda | Shabunda |
|  |  |  | Uvira | Uvira |
|  |  |  | Walungu | Walungu |
| 9 | Tanganyika | 6 | Moba |  |
|  |  |  | Manono |  |
|  |  |  | Kabalo |  |
|  |  |  | Kongolo |  |
|  |  |  | Nyunzu |  |
|  |  |  | Kalemie |  |
| 10 | Tshopo | 7 | Opal |  |
|  |  |  | Yahuma |  |
|  |  |  | Ubundu |  |
|  |  |  | Forest |  |
|  |  |  | Banalia |  |
|  |  |  | Bafwasende |  |
|  |  |  | Isangi |  |
| 11 | Tshuapa | 6 | Befale |  |
|  |  |  | Djolu |  |
|  |  |  | Bokungu |  |
|  |  |  | Accommodations |  |
|  |  |  | Ikela |  |
|  |  |  | Monkoto |  |
| Total Territories |  | 54 |  |  |

- Multi-ltipartite strategic partnerships  Partnerships with provincial administrations and  local authorities, private operators and non-state actors will be established  for the construction of infrastructure and equipment, the strengthening of  managerial and technical capacities, as well as for communication, awareness-raising and mobilization of actors at the    community level. .  This will require an ex-ante assessment of the capacities of each partner to determine appropriate partnership modalities with UNDP.

- Sustainability and sustainability of the program.  Capacity building will be a fundamental constant in the implementation of the Programme. It will consist of strengthening the local development management capacities of actors at the provincial and local levels and defining a national reference system for trades at the provincial and territorial levels. Capacity-building of key actors will need to be part of an empowerment approach.

- Complementarity and synergy with other programmes. UNDPwill ensure that PDL-145T collaborates and complements other existing and similar sector  programmes.  It will therefore not duplicate interventions already planned and planned under these ongoing sectoral programmes.  The implementation of the Programme at the provincial level will therefore align, as far as possible, with Provincial Development  Plans and Local Development Plansfocused on the SDGs and their priority targets.

- South-South partnership.  Successful exchanges of experience through South-South cooperation will be envisaged to capitalise on the experiences and good practices of African countries in local development and the fight against poverty and inequalities.

- Integration of transversal dimensions.  The Programme will integrate at all stages of its implementation cross-cutting dimensions such as gender equality and equity, youth, climate change adaptation and mitigation, and respect for human rights. Specific results in each of these three dimensions will be taken into account in the Programme's results chain, depending on the specificities of rural and peri-urban areas.

- Priorities given to the creation of income-generating jobs.  Priority will be given to the implementation of infrastructure and works with a high intensity of local labour. The jobs thus created will make it possible to distribute income to local populations, particularly young people and women. This approachwill contribute, in addition to the implementation of the programme, to the training and socio-occupational integration of the active populations mobilized. Part of the income distributed to local populations thanks to the work carried out in return, can be invested by the beneficiaries to acquire either assets to develop rural entrepreneurship, or decent housing.

- Strengthening of the communication aspect of the Programme.  A capitalization and communication strategy will be developed to document successful practices and experiences to be scaled up, and to ensure stakeholder mobilization  and visibility of the results of the Programme, as well as political commitment to poverty and inequality reductionby the government.

- Anational ownership and community participation.  The participation, national ownership and empowerment of women, youth and community groups, in particular, in the implementation of the Programme will be a top priority for UNDP. Collaboration with the authorities will continue throughout the implementation of the Pprogramme. Territorial and local authorities will be informed of the interventions to be carried out in their respective localities   and will be actively involved, as necessary,  for the  success and sustainability of the achievements. The communities will be involved in the implementation of the Programmethrough  the various  activities  of training, awareness-raising, participation and monitoring of the achievements of the  Programme. The ownership and empowerment of populations will be particularly aimed at strengthening their needsand ensuring the provision of assets that facilitate their self-care.

# Prerequisites for the successful launch and implementation of the programme

- The successful launch and implementation  of  the Program requires that the   following prerequisites be met:

- The Government and UNDP will jointly define an intervention strategy, specific to each province, taking into account constraints related to accessibility, security, etc.  in each of the intervention areas.

- The Government  will disburse the funds according to the timetable set out in the financing agreement, which will be backed by the technical implementation plan ofthe programme. The consequences of delays and non-timely disbursements of these funds arenot the responsibility of UNDP.

- The Government focal point  (SPC, CONA, CTSP, CPTP) acting as an interface between UNDP and the Governmentmust be clearly designated through official channels (Ordinance, or Decree or Order).  In this respect, the governance and monitoring bodies of the Programme and  the official technical structure of  the Government must be set up before or as soon as the  Programme is launched;

- The three implementing agencies of PDL-145T (UNDP, BCeCo, CFEF) will collaborate and work in synergy and intelligence to ensure the achievement of Program results;

- The UNDP  Management Unitwill be set up as soon as the Programme is launched.  Its deployment will begin with a  small (core) team  ; the  rest of the team will be mobilized as the programmegrows.

- The rapid start of implementation of the programmewill depend on  the availability of  all the technical documents to be provided by the services of the various ministries concerned or, failing that, through feasibility studies to be carried out prior to the construction of the  infrastructure. These documents include:

    - Topographical surveys carried out onthe planned sites;

    - Specifications, technical specifications and referenceterms of the activities and investments to be carried out;

    - Accessto existing databases;

    - Hydraulic and electrical maps;

    - Dhe architectural model projects for buildings, schools, health centres

    - As well   as any other relevant documents concerning the various components of the Programme.

These studies will be confirmed and  validated by a joint field visit which will specify the targets, sites and actual costsof the various structures.

- If the designated units of the respective sectoral ministries are unable to provide the feasibility studies, UNDP will commission them from the relevant external partners. The related costs will be borne by the PDL-145T budget and will be added to the construction costs of the infrastructure concerned. These private studies will also be validated and confirmed by the structure, the government's  technical focal point for this project.

- Tender documents will need to be validated by the national counterpart (technical committee) with respect to technical specifications, locations, locations, and nature/quantity of the works before the recruitment process forUNDP consultants   and implementing partners is initiated by UNDP in accordance with its rules and procedures.

- In cases where the above preconditions  (i) and (v) are not fully met or made available, it would be necessary for both parties to review  and possibly revise some of the planned activities to take into account the level of funds currently available and the availability and quality of technical documents received.

# RESULTS AND PARTNERSHIPS

# Program Expected Results

- Overall,the Programme will produce the following four transformational outcomes (or effects):

OUTCOME 1:  Access  to basic socio-economic infrastructure and services for the populations of the 54 territories is significantly improved.

- Overall, this outcome will contribute to correcting spatial inequalities, and reducing the multiple deprivations faced by rural populations, through improved access to basic social services.  The main expected effects will result from the products and activities that will be generated by the construction/rehabilitation of basic socio-economic infrastructure, including health, education, access to electricity, water and agricultural feeder roads. The so-called local labour-intensive approach will be favoured. In terms of construction or rehabilitation of health infrastructure, the project will build/rehabilitate 283 functional health centres in the 54 territories. It will supply water and electricity to all health facilities.

- The number of people with access to health care will need to double between 2021 and 2023. Unnecessary suffering and premature deaths from preventable and treatable diseases will be reduced. Life expectancy at birth in the DRC is expected to converge towards the average in Sub-Saharan Africa (60 years). The accumulation of a stock of human capital, necessary for the management of local development, will be ensured. As for school infrastructure, 423 primary schools will be built and equipped in 66 territories,  which will train 600,000 children, at least 40% of whom are girls.

- Access to a reliable and regular source of energy will be ensured by the construction of micro-hydroelectric and solar power plants. This will connect at least 10 million Congolese living in rural and peri-urban areas  of the 66 territories to an energy source. Beyond the direct access of populations to electricity for domestic needs, activities such as the processing and conservation of  agro-pastoral products, better functioning of health and education services, the supply of hydraulic works, will be boosted by improving the supply of energy services in rural areas.

- The Programme aims to ensure access to  a  source of drinking water for 10 million  Congolese living in the 66 rural territories (1 million m3 per day in rural areas). To this end, it will proceed to the construction / rehabilitation of 274 developed water sources, thanks to 1070 boreholes that will be erected. The rate of access to drinking water will grow by 15% annually between 2020 and 2023. This will reduce the prevalence of preventable waterborne diseases, while improving the level of food and nutrition security.

- For women, who in rural areas are often forced to travel several km to get supplies, this will save a lot of time and reduce the need to fetch water. The time saved will be used for income-generating activities, education and child care.

- Rural populations' access to a better transport  system for people and goods will be effective through the construction/rehabilitation of 16,060 kilometres of rural agricultural feeder roads. Opening up the provinces and territories will link agricultural production centres to processing and consumption centres. It will make it easier for Congolese to move within the country. This promotes national integration and the feeling of territorial continuity and social inclusion of all Congolese.

RESULTS 2 : The economies of rural territories are revived and boosted

- The effects attached to this result are the development of stable and decent sources of income, the adoption of resilient and sustainable agricultural systems, the creation of agricultural and forestry value chains, the establishment of cooperatives and socio-professional groups, the creation of rural jobs through the promotion of innovative solutions by young people and women and a better organization of production and marketing systems.

- The main targeted results in terms of agro-pastoral production and processing facilities are: (i) the development of 75 ha on average per territory and by speculation. A total of 16,200 ha will be developed in the 54 territories for 4 speculations.  These community production areas will be equipped with tractors and agricultural processing equipment. According to the priorities identified at the base, intensive agricultural production under management will be structured around main speculations such as maize, cassava, groundnuts, beans, sweet potatoes, potatoes, soybeans, rice and perennial crops.

- A production subsidy for about 300,000 most vulnerable households will be  allocated, basedon priority choices, which will be identified by the producers themselves during the rural animation process during  the first months following the launch of  the Programmein the 66 months.  Territories. This may include the acquisition of agricultural inputs and seeds, motorized tricycles, and pairs of oxen with accessories and transportation in the 66 territories. Finally, part of the support will be directed towards the promotion of innovative local solutions through the support and supervision of start-ups at the grassroots level. To this end, national research structures will be used. These results will generate more than 1 million jobs.

- The realization of agro-pastoral value chains will be facilitated by the creation of thousands of very small and small enterprises in various sectors that may include the production of green charcoal, biogas and paving stones; warehouses; cold rooms and drying centers for agricultural products; functional energy distribution companies; distribution of at least 3 million tons  of seeds selected per year; 1 business incubator created per territory. In total, at least 10 agro-sylvo-pastoral value chains will be developed in each territory  in line with the economic potential of the province.

- To enable rural populations to maintain a dynamic of self-organization through cooperatives and socio-professional groups, about 500 cooperatives and Economic Interest Groups (EIG), as well as 130 socio-professional associations will be set up.

- Access to the decentralized financing system, particularly microfinance, will involve support for the opening of accounts, between 2020 and 2023, in microfinance institutions located in rural and peri-urban areas. To this end,  the Programmewill establish partnerships with other projects and programmes with a similar vocation for the establishment of lines of credit.

RESULTS 3 : The local development management capacities of territorial and community state actors are strengthened

- This result is expected to effectively establish  institutional and organizational instruments and mechanisms for development management at the local level. These instruments and mechanisms will produce effects relative to the effective implementation at the local and provincial levels of public policies capable of addressing social demand and making the rule of law effective against the background of the broader process of restoring the authority of the State, whose physical presence in all 89 territories will henceforth be effective with the construction by the P. Program of administrative buildings and decent  housing for the governing staff of the territories.

- The four categories of actors that will be targeted are provincial administrations for the management of projects and programs; local authorities for the monitoring of construction or rehabilitation of socio-economic infrastructure and the promotion of local economies; cooperative groups and socio-professional associations for the mastery of technical itineraries of crops and value chains; organizations and associations of agro-pastoral and local service providers to trigger a community dynamic of development at the base essential to complement the interventions of public administrations.

- The strengthening of local  development planning and management functions will be supported by the Programme and will concern each  of the 25 provinces that will be endowed, from the first year of implementation of the Programme: (i) Planning-Programming-Budgeting-Monitoring-Evaluation (PPBSE) chains;  (ii) Provincial units in charge of partnerships and resource mobilization;  (iii) Public procurement units;  (iv) Monitoring and evaluation systems;  (v) System for the production of statistical information;  (vi) Local Development Plan;  and (vii) Provincial Accountability Systems.

- Capacity building in project management/implementation of basic socio-economic infrastructure works will be effective through training in project management of provincial and local administrations, support for the creation of 725 community organizations providing local services, raising awareness among 500,000 people about entrepreneurial culture, user behaviour for good operation and   infrastructure maintenance. The capacities  of community-based organisations and community-based service providers will also be strengthened in the areas of infrastructure operation and  maintenance to ensure its sustainability after the end of the programme.

- The establishment in fragile provinces of institutional capacities to prevent or mitigate violations of fundamental human rights will be facilitated through the implementation of a communication-awareness-raising campaign by province and per year during the implementation of the programme. Biannual human rights training sessions in each of  the 25 provinces will also be organized and supported by the Programme.

- Annual land management training campaigns will be implemented in each province to develop local capacity in: (i) long-term land management; (ii) land and natural capital management; and (iii) promotion of production and management systems for certain rural facilities (Input Storage Stores; Market gardening wells; Cultural techniques; Agricultural product processing platforms; Weekly markets).

RESULTS 4 : An interoperable geo-referenced monitoring information system is developed and made operational

- This outcome will contribute to:

- The establishment of a geo-referenced information system centralizing all data relating to PDL-145T and interoperable with existing national systems;

- The realization of a mapping of the various achievements of PDL-145T and the indicators for monitoring public policies and programs;

- Facilitating access, sharing and dissemination of Programme information to all stakeholders through a user-friendly interface;

- The development of communication materials on the activities of the Programme;

- The strengthening of the technical capacities of the staff of the structures involved in the use of the system from the local to the central level.

- As part of this result, the Programme will also strengthen the institutional capacities of central and decentralized administrations in monitoring and evaluation of development programmes and projects by providing them with the necessary tools and computer equipment.

# Partnerships

- UNDP will promote technical partnerships in the implementation of programme activities. In this sense, it will mobilize, as far as possible, available national and international expertise, public services, local authorities and the private sector, as well as civil society organizations, in the implementation of the specific segments of PDL-145T, as implementing partners of UNDP, subject to their legal statutesso permitting. With equal competence, priority will be given to thex Congolese contractors and subcontractors.

# Sustainability and scale

- From the outset, UNDP will involve the competent  decentralized structures of the State and those  of the local authorities in the implementation  of the Programme and,  along the way, will transfer  powers to the national sector to ensure quality succession at the end of its mission, particularly as regards    management of basic infrastructure and services, procurement, management of contractual relations with entities operating at the base. The  Programme will favour the cluster approach, the inclusion of all actors and the implementation of the social mobilisation and training strategy for better ownership and sustainability of the Programme. The principle of sustainability of interventions and investments, taking into account the possibilities of scaling up, will guide the optimal implementation of the Pprogramme.

# RESOURCES AND RESULTS FRAMEWORK

# Resources required to achieve expected results

- The financial resources for the implementation of the program will come from the Congolese State budget. Financial and technical partners will be mobilized as soon as possible to contribute financially to the implementation of the programme. UNDP will contribute its expertise, expertise and expertise in the implementation of development programmes. It will also contribute to its strategic positioning on the national territory, by mobilizing its field offices, and by developing synergies and complementarities with its various similar programs currently being implemented. Its African and international network of consultants and its various implementing partners, as well as UNDP country offices that have already conducted such programmes, will also be involved.

- The total cost of PDL-145T is estimated at  US$  1.66 billion. The budget portion of the Programme to be implemented by UNDP is estimated at USD  619,829,499 (USD Six hundred and nineteen million eight hundred and twenty-nine thousand four hundred and ninety-nine).  This cost will cover the two years of the programme(2021-2023).  The budget will be disbursed to UNDP according to the disbursement schedule annexed to the financing agreement to be signed between the Government of the DRC and UNDP. As already stressed, UNDP will mobilise the appropriate expertise for the implementation of the various components of the Programme. UNDP will ensure that contributions are effectively available for the implementation of planned activities. The contribution for cost-sharingmust include a prorated share of the  General Management  Service fee  of 3.5%, as well as the direct costs related to the management of the programme indicated in  the budget of the Programme (both not exceeding 7% of  the total  amount allocated to the Agency). .

TABLE 2: PROGRAM BUDGET

| Descriptions (Components/Activities) | Total cost | Parts |
| --- | --- | --- |
|  | (in USD) |  |
| Component 1: Development of basic socio-economic infrastructure | 434. 939. 195 | 69% |
| Component 2: Rural Economy and Value Chain Development | 108. 000. 000 | 17% |
| Component 3: local capacity-building | 4. 940. 000 | 1% |
| Component 4: Geo-referenced system for monitoring | 5. 540 000 | 1% |
| TOTAL COMPONENTS (1+2+3+4) | 553. 419. 195 | 88% |
| Program Management Fees | 38. 739. 344 | 7% |
| Studies and contingencies (5%) | 27. 670. 960 | 5% |
| TOTAL PROGRAMME | 619. 829. 499 | 100% |

# Resources and Results Framework

TABLE 3: Articulation of the PDL-145T results chain

ACTIVITIES ACTIVITIES; PRODUCE PRODUCE; BELONGINGS BELONGINGS; IMPACT IMPACT. - Rehabilitate and maintain agricultural service roads and engineering structures respectively; - Electrifying sectors by solar means and public lighting by solar street light - Rehabilitate and maintain agricultural service roads and engineering structures respectively; - Electrifying sectors by solar means and public lighting by solar street light; 1.1. Road and energy infrastructure are built and/or rehabilitated 1.1. Road and energy infrastructure are built and/or rehabilitated; 1. Better access for populations to basic socio-economic infrastructure in rural areas, in the 145 territories 1. Better access for populations to basic socio-economic infrastructure in rural areas, in the 145 territories; Significantly and sustainably improve the socio-economic framework and living conditions of rural populations Significantly and sustainably improve the socio-economic framework and living conditions of rural populations. 2. Better access of populations to basic social services (health, education) 2. Better access of populations to basic social services (health, education). - Build, rehabilitate and equip Health Centers - Build, rehabilitate, complete and equip Primary Schools - Build boreholes with bollards and develop water sources - Build, rehabilitate and equip Health Centers - Build, rehabilitate, complete and equip Primary Schools - Build boreholes with bollards and develop water sources. - Acquire and make available certified seeds and quality inputs to producers in the various priority sectors - Development and equipment of areas for production and processing in priority sectors - Acquire and make available certified seeds and quality inputs to producers in the various priority sectors - Development and equipment of areas for production and processing in priority sectors; 2.1. Producers have received support for inputs and equipment and increased their production 2.1. Producers have received support for inputs and equipment and increased their production; 1.2. Water, health and educational infrastructures are built and equipped 1.2. Water, health and educational infrastructures are built and equipped; 3. Increased incomes of producers in the programme intervention area and improved food security 3. Increased incomes of producers in the programme intervention area and improved food security. - Train the actors of the Territories; - Building the capacity of organizations - Train the actors of the Territories; - Building the capacity of organizations; 3.1. Programme actors are informed, sensitised, trained and strengthened in their capacities 3.1. Programme actors are informed, sensitised, trained and strengthened in their capacities.

| Effect of the 2019-2023 NDSP & Axes |  |  |  |
| --- | --- | --- | --- |
| Effets UNSDCF & CPD |  |  |  |
| Expected impact of the programme |  |  |  |
| Strategic Partners |  |  |  |
| Title & identification number of the programme | N° ATLAS-AWARD |  |  |
| Expected outputs | Indicator targets | Indicative activities | Indicative costs Globaux |
| Component 1 | Improving access to basic socio-economic infrastructure and services |  | USD 434. 939. 195 |
| Expected effect | Poor rural and peri-urban populations have better access to basic socio-economic infrastructure and services |  |  |
| P.1.1. : Primary schools are built, equipped and functional. Indicators: - Number of classrooms built/rehabilitated and equipped; - Baseline situation: | - 423 primary schools built or rehabilitated and equipped in 54 territories 300,000 children, at least 40% of whom are girls; - Gross enrolment rate of at least 50 per cent in the target territories and sectors, starting in the second year of implementation of the Programme. | - Inventory of technical studies available at the provincial level; - Completion of all required preliminary technical studies; - Preparation and publication of Tender Documents (DAO); - Awarding of contracts; - Contractual arrangements with construction companies; - Monitoring and control of work sites; - Acquisition of classroom equipment; - Establishment of local management committees; - Monitoring, control and evaluation of the works; - Acceptance of works; - Reception and commissioning of built/rehabilitated infrastructures. |  |
| P.1.2. : Health centres are built, equipped and functional. Indicators: - Number of health facilities built and equipped; - Number of mutuals; - Baseline | - 283 functional health centres in 54 territories - An additional 3 million Congolese have access to a local health service in the areas of intervention; - 90% of health facilities in the project's 54 intervention territories are supplied with water by 2023. | - Preliminary studies or updating of standard models; Technical specifications - Preparation and launch of DAO; - Attribution and Contractualization with companies; - Acquisition of equipment for health centers Monitoring and control of electrification works; - Acceptance and commissioning |  |
| P.1.3. : Agricultural service roads and engineering structures are built and functional. Indicators: - Linear of constructed and functional rural agricultural feeder roads. - Baseline situation : | - 28,330 kilometres of rural agricultural feeder roads; - 10 million Congolese have access to a transport system; | - Preliminary studies or updating - Preparation and launch of DAO; - Attribution and Contractualization with companies - Acceptance and commissioning |  |
| P.1.4. : Electricity networks are set up and functional. Indicators: - Number of electrified sectors per territory; - Number of rural households with access to electricity; - Baseline situation: | - 172 micro solar power plants are built and functional - 168 km are illuminated by solar street lights in the 54 territories of intervention of the project - 5 million more Congolese benefit from electrification | - Preliminary studies or updating and choice of rural electrification options; - Preparation and launch of DAO; - Attribution and Contractualization with companies; - Monitoring and control of electrification works - Acceptance and commissioning |  |
| P.1.5. : Rural water infrastructure is built and functional. Indicator: - Number of boreholes / standpipes built; - Number of villages supplied by water infrastructure built. - Baseline situation: | - 1 millionm3 of water per day is injected into water distribution networks; - 15 million Congolese have access to drinking water; - 266 water sources developed; - 1070 water boreholes completed; | - Preliminary studies or updating and choice of sites; - Preparation and launch of DAO; - Attribution and Contractualization with companies; - Acquisition of pumping equipment - Monitoring and control of electrification works; Acceptance and commissioning |  |
| P.1.6. : Housing of the administrative authorities are built and inhabited Indicators: - Number of dwellings: - Number of functional administrative buildings Baseline situation: | - 307 building constructions of which - 54 administrative buildings of the Territorial Administrators; -253 administrative buildings of the Heads of sectors -540 dwellings of the administrative authorities of the territories; | - Preliminary studies or updating of architectural models; - Preparation and launch of DAO; - Attribution and Contractualization with companies; - Acquisition of equipment for administrative buildings - Monitoring and control of electrification works; - Acceptance and commissioning |  |

| Component 2 | Promoting rural economies and value chains |  | USD 108. 000. 000 |  |
| --- | --- | --- | --- | --- |
| Expected effect | Rural populations use efficient techniques and equipment for the production, processing and marketing of products as well as financial services to improve their productivity with a view to increasing their incomes. |  |  |  |
| P.2.1. Agricultural production and processing equipment is available. Indicators: - Number of equipment distributed to producers / women / men. - Baseline situation: | - 42,640 product processing units; - 7. 625 motorized tricycles; - 16. 200 ha developed in the 54 territories for at least 4 speculations due to an average of 75 ha per perimeter developed by speculation; | - Realization of studies of identification of requests and technical options - Preparation and launch of DAO; - Assignment and contracting; - Acquisition of agricultural and post-harvest production equipment; - Acquisition and distribution of improved seeds; - Construction / rehabilitation of storage warehouses; |  |  |
| P.2.2. Agro-sylvo pastoral value chains are created and supported. Indicators: - Number of agro-pastoral value chains created by province: - Baseline situation: | - 300. 000 tons of seeds selected and inputs per year and distributed to producers; - At least 1 incubator created per territory; - 10 agro-sylvo-pastoral value chains in each province. | - Realization of studies to identify agro-sylvo-pastoral value chains; - Preparation and launch DA for the recruitment of support structures; |  |  |
| P.2.3 Cooperatives and socio-professional groups are created and supported. Indicator - Number of cooperatives / socio-professional groups created by province: - Baseline situation: | - 500 cooperatives and Economic Interest Groups (EIGs); - 260 micro-power grids; - 130 socio-professional associations will be set up. | Consultation with stakeholders; - Identification of needs for community organizations; - Support for the establishment of cooperatives / socio-professional groups. |  |  |
| Component 3 | Strengthening local development management capacities |  | USD 4,940,000 |
| Expected effect | Local development management capacities are strengthened at the local and community levels. |  |  |
| P.3.1. Training in development planning and management is provided. Indicators: - Number of strategic planning training modules delivered: - Number of training modules in local development management delivered: - Number of women/men trained: - Baseline situation: | - 25 Monitoring and evaluation systems; - 25 Planning-Programming-Budgeting-Monitoring-Evaluation (PPBSE) chains; - Art. 25 Public procurement units - Statistical information production system; | - Conducting studies to identify provincial training needs in local development management; - Development and launch of DAO for the recruitment of operators; - Identification of actors to be trained; - Training of actors in strategic planning and project management. | USD 1,040,000 |
| P.3.2. Training in project management / works work is provided. Indicators: - Number of training modules delivered by province: - Number of women/men trained in project management/work - Baseline situation: | - 25 training courses (1 per province) in project management; - 02 training modules delivered per year in each province; - 30% of young people trained in project management/work work; - Formation of local development committees | - Realization of studies to identify provincial training needs in project management in the territories; - Development and launch of DAO for the recruitment of operators; - Identification of the actors to be trained and development of an implementation schedule; | USD 1,000,000 |
| P.3.3. Training and capacity building in the operation, upkeep and maintenance of community and private structures (boreholes, developed water sources, solar street lights, solar power plants, health centers, etc.) are provided. Indicators: - Number of training modules delivered by province: - Number of women/men trained in project management/work Baseline - Number of exchange visits made | - 1450 community-based organizations providing community-based services are strengthened in terms of infrastructure management, operation and maintenance; - At least 30% of those trained are women and at least 60% are young people under 30 years of age; | - Realization of studies to identify training needs in project management in the territories; - Identification of state and non-state actors (NGOs, private individuals) active in the target sectors in the territories and provinces of intervention; - Signature of partnership agreement - Identification of the actors to be trained and development of an implementation schedule; - Organization of exchange visits | USD 1. 600. 000 |
| P.3.4. Capacity to prevent human rights violations is strengthened. Indicators: - Number of training modules on the prevention of human rights violations delivered by province: - Number of human rights awareness campaigns conducted by province: - Baseline situation: | - Awareness raising by province and year; - 4 Communication campaigns - 8 training modules (2/year) on human rights in each province | - Communications / awareness-raising on violations/deprivation of fundamental human rights, gender inequalities and inequities - Development of partnerships with human rights and gender equality groups; - Training of decision-makers / Customary chiefs / opinion leaders / security personnel; | USD 1. 300. 000 |

| Expected outputs | Indicator targets | Indicative activities | Global indicative costs |
| --- | --- | --- | --- |
| Component 4: | Setting up an interoperable geo-referenced monitoring information system |  | USD 5. 540. 000 |
| Expected Impact: | The system for information, geolocation and monitoring and evaluation of infrastructure and equipment provides information on the progress of the PDL and serves as a national reference for monitoring public policies and programs throughout the country. |  |  |
| P.4.1. An interoperable geo-referenced information system for monitoring the LDP is set up | A geo-referenced monitoring system is set up | -State of play and needs analysis -Review of existing national information systems - Development of ToR for the choice of the operator in charge of the implementation of the GIS; -Development of partnerships/LOA with public and / or private structures involved in the field of management, production of geographic information - Establishment of a technical subcommittee in charge of accompanying the process -Choice of software equipment / servers to acquire for GIS -Preparation of DAOs - Launch of the equipment acquisition process - Choice of an operator in charge of the implementation of the GIS Framing, orientation and validation workshop with the operator | USD 724. 000 equipment (4. 000 USD x 145 territories; 4. 000 USD X26 provinces and 4. USD 000 X 10 central government) USD 150. 000 for the map server and its components (software) USD 200. 000 for the operator in charge of setting up the GIS USD 150. 000 for the operator in charge of deploying and distributing the platform USD 3. 216. 000 Image acquisition and various studies |
| P.4.2. The mapping of the achievements of the PDL is carried out regularly | Dynamic and interactive mapping products are available | -Validation workshop of the georeferenced database - Validation workshop of the GIS prototype for deployment - GIS and cartographic products validation workshop -Definition and validation of the modalities of updating and the conditions of access to the database and the GIS by the users | USD 100. 000 for technical workshops at national level (1 workshop at USD 50. 000 and 2 workshops at USD 25. 000) |

# MONITORING MECHANISM – EVALUATION AND AUDIT OF THE PROGRAMME

- Program results as described in the Project Results Framework will be monitored and reported on a  quarterly basis and evaluated periodically during implementation to ensure that the Program is on a trajectory to effectively achieve its outcomes.

- Monitoring activities will use the set ofindicators selected to: (i) collectand analyse data on progress against the RRF outcome indicators in order to determine  the progress made by the Programme towards the achievement of agreed outputs; (ii)  assess the level of U  and the  degree of technical and physical conformity of the activities carried out or in progress with what was planned by the initial planning; (ii) to detect discrepancies, according to the periods, between the level of actual achievements and the forecasts; (iii) analyze the reasons for such discrepancies; (iv) make the necessary adjustments.

- A monitoring system for the Programme will be set up and will be run on a quarterly, half-yearly and annual basis. A bridge will be established between the performance monitoring/evaluation system of the PDL-145T and the geo-localized information and monitoring/evaluation system for infrastructure and equipment. The entire system will be supported by the UNDP regional service centre in Addis Ababa and/or headquarters.

- Evaluation will consist of a rigorous and independent assessment of the physical, technical and quality activities carried out or in progress, to determine the level of achievement of the objectives set and contribution to decision-making.

- A first independent evaluation of the Programme will be carried out mid-term according to international standards and/or UNDP procedures. A final evaluation will be conducted at the end of the implementation of the Program. The evaluations should make it possible to objectively assess the results, the constraints of implementation and to indicate any reorientations necessary to achieve the results of the Programme. The results of these evaluations, together with the related recommendations, are submitted to the National Operational Coordination  Committee on .

- The mid-term review and evaluation will be organized in accordance with mutually agreed arrangements between the Government and PUND. The members of the independent external evaluation team will be appointed in accordance with the profile required by the Mission's ToR.

- The various evaluation reports, and in particular their conclusions and recommendations, are intended to support appropriate decision-making to improve effectiveness and efficiency in the implementation of the Programme. A schedule of these various evaluation and audit exercises will be drawn up in collaboration with the Programme Management Unitand will be the subject of the Programme's scoreboard or work plan. The entire system and the programme monitoring and evaluation system is based on results-based management (RBM), in accordance with UNDP norms and standards;

- Learning and knowledge.   Similarly, on an annual basis, knowledge, good practices and lessons learned will be periodically documented from  Programme activities as  well as from others collected from other projects and partners and reintegratedinto the Programme as appropriate.

- Internal audit and financial control of the accounts of the Programme will be carried out in accordance with UNDP terms and conditions.  Anexternal audit could be commissioned according to the modalities agreed between the two parties.

# INSTITUTIONAL ARRANGEMENTS FOR GOVERNANCE AND PROGRAMME MANAGEMENT

# Arrangements for the management and control of the programme

- The Political Steering of the Programme is placed under the direct supervision of the President of the Republic. The Prime Minister ensures the Strategic Management of the Programme while the Operational and Technical Coordination of the   Programmeis placed under the supervision of the Minister responsible for the Plan.  The Programme  will be implemented under the "Direct Execution" modality, UNDP manages it and will report on the expected results of its intervention.  UNDP will use implementing partners and/or subcontractors to implement some of the Programme's activities. It will provide the programme with technical staff who will rely on sectoral ministries and certain technical structures in order to ensure the continuous availability of their services.

- UNDP will ensure the recruitment of PMU staff, the administration of staff contracts, the initiation and start-up of activities and the preparation of annual work programmes and budgets (AWBPs). UNDP will contract with contractors in accordance with its procurement procedures.  The establishment of the steering committee and the technical committee will be the responsibility of the government side in accordance with the institutional framework for the implementation of PLD-145T.

- In addition, the technical ministries concerned will be involved in the entire implementation process, including the development and validation of technical specifications in accordance with the modalities adopted in the programme. (cf PL  PLD-145T  on Executing Agencies)

- In the implementation of the various components of the Programme, UNDP will have to collaborate with the national technical structures and institutions under the line ministries of the areas covered by PDL-145T through letters of agreement that will be signed with these entities, as well as with NGOs, associations, groups and private actors through calls for competition. Particular emphasis will be placed on the participation, empowerment and empowerment of local  communities in achieving the objectives.

# Programme management and coordination

- The Programme has a four-level management structure:  a   Political Governance Committee (PPC), a Strategic Steering Committee (SPC), a National Operational Coordination  (CONA), and a Programme Management Unit  (PMU) attached to UNDP.

- The political steering of the Programme will be ensured directly by and under the leadership of the President  of the Republic. The strategic steering of the programme isplaced under the direct authority of the Prime Minister, Head of Government. And the operational and technical coordination  of the implementation of the Programmewill be the responsibility of the Minister of Planning.

- The mandates and modalities of operation of each body will be defined by a Presidential Ordinance.

# Political Steering Committee (CPP)

- The Strategic Steering Committee (SPC) will be chaired by the President of the Republic. The CP P will hold four regular meetings per year and extraordinary meetings on the initiative of its Chairman according to the needs of the Programme.

- The Political Steering Committee has, among other mandates, to:

- Ensure the political support of the program at the highest level;

- Provide guidance to the Strategic Steering Committee;

- Advocate with Technical and Financial Partners (TFPs) and private individuals at the highest level to mobilize financing for PDL-145T.

# Strategic Steering Committee (SPC)

- The CPS is placed under the leadership of the Prime Minister, Head of Government. It will hold twelve regular meetings per year and extraordinary meetings on the initiative of its President according to the needs of the programme.

- The Strategic Steering Committee  has, among other mandates, to:

- ensure the coordination of the programme, projects and arrangements contained in the programme;

- ensure the general monitoring of the implementation of the programme;

- instruct the disbursements of PDL-145T resources and their allocations to executing agencies;

- define programmatic directions for the implementation of PDL-145T;

- ensure accountability to the legislature;

- monitor the resource mobilization strategy internally and with technical and financial partners;

- sign contracts with Executing Agencies;

- validate the PDL-145T Work Plan and Annual Budget;

- approve the various management reports of PDL-145T;

- organizes evaluations and audits of the Programme.

# National Operational Coordination (CONA)

- The national operational coordination of the programme is under the supervision of the Minister in charge of Planning.  CONA will meet twice a month and whenever necessary.

The CON will be responsible for:

- Monitor the implementation of the Programme by the selected implementing agencies;

- Initiate control missions through the institutional control and audit services and Validate their reports;

- Prepare advocacy for the mobilization of external resources of TFPs that have subscribed to the financing of PDL-145T;

- Monitors disbursements of resources to programme implementing agencies;

- Coordinate communication on the Program;

- Report to the Strategic Steering Committee on the constraints, blockages noted in the implementation of the program, and suggest relevant solutions;

- Support provincial technical committees in monitoring Program activities;

- Validate the work plan to ensure the physical advancement and consumption of the budget allocated to PDL-145T at the level of executing agencies;

- Validate the implementation reports prepared by the Technical Committee and provide relevant guidance for better implementation;

- Provide all necessary support and facilities to the implementing agencies for effective and efficient implementation of the Programme.

- CONA will be assisted by a Technical Committee of the Programme Council (CTSP). The SP TC will play the role of the Technical Secretariat of the CONA. It is set up by Ministerial Order of the Minister of Planning and includes a Coordinator, a Deputy Coordinator and the Experts appointed by the Minister responsible for the Plan.

# The Provincial and Territorial Monitoring Committee (CPTS)

- In accordance with the government's decentralization strategy, the governors' offices and the relevant provincial  ministries will play an important role and will constitute a Provincial and Territorial Monitoring Committee (CPTS). It is installed in each territory by an Edict of the Provincial Governor  and will include:

- the Provincial Minister responsible for the Plan;

- the Head of Provincial Planning Division;

- the Head of the Provincial Rural Development Division;

- the Administrators of the Territory;

- Heads of Sector/Group;

- the representative of the Customary Chiefs;

- the representative of Civil Society.

The CPTS will be coordinated by the Provincial Governors.

Their missions are  :

- Facilitate theexecution of the work to be carried out by the contractors hired by the implementing agencies under a memorandum of understanding between these agencies and the Central Government;

- S the progress of thework at the level of each territory;

- Toidentify and advise the executing agencies in the implementation of the integrated master plan for the production of the work operation plan by the contractors.

# Program Management Unit (PMU)

- The day-to-day management and facilitation of the Programme's activities will be carried out by the Programme Management Unit (PMU), under the supervision of UNDP. The PMU will be housed in UNDP and will provide all project management functions for the programme components. It will be composed of a Senior Technical Advisor, a National Coordinator, an Operations Specialist, a Risk & Quality Control Officer, a Legal Officer, Civil Engineering, Energy, Agronomy and Hydraulics Engineers, EnvironmentalSpecialists , Value Chain, Community Development, Results Based Monitoring and Evaluation,  communications, financial and procurement specialists and support staff (see proposed organizational chart in annex). Staff terms of reference will be developed. They will be recruited according to UNDP procedures.

- UNDP will provide essential technical, financial, monitoring and quality assurance functions in all programme activities to ensure efficiency, effectiveness and overall value for money. The Program will bear all direct costs (CPD) related to its implementation.

- To ensure coordination at territorial level orclose presence at the intervention sites of  the Pprogramme, Provincial Intervention Agencies (BPIs) will be set up in the 15 intervention provinces. They will work under the direct supervision of a provincial coordinator, who in turn will report directly to the PMU  team based in Kinshasa.  With a view to ensuring ownership  of the Programme by the CPTS, the  ICBs will work closely with the CPTS of the Programme. These CPTS will be used in the preparation of annual work programmes, monitoring and evaluation of the Programme and raising awareness among beneficiaries and other stakeholders  .

# Procedures for recruiting and acquiring goods and services

- Once the work plan has been adopted by the Steering Committee, the Management Unit, as an integral part of UNDP, will proceed with the launch of the acquisition and recruitment process. The acquisition will be carried out in accordance with UNDP rules and regulations. To achieve the expected results in the near future, exceptional procedures (fast-track) will be used.  Due to the pressure to achieve immediate results, the orthodoxy of the rules of direct execution by UNDP should be observed flexibly, in consultation with UNDP headquarters, to allow the use of exceptional measures to, for example, acquire and secure scarce expertise and capitalize on opportunities to move quickly in implementation.

- All these expected accomplishments will be achieved only through a capital of trust that UNDP should build with service providers for the execution, monitoring and   quality control of the work of the various technical aspects of theProgramme. This capital of confidence will be maintained throughout the implementation of this programme, thanks in particular to the  mobilization of resources by the competent State services, in real time, and in accordance with agreed payment schedules to avoid delays in the payment of service providers' invoices.

- The LDP 145T Program Document  made the following arrangements:

  - On the instruction of His Excellency the Prime Minister, a sub-account of the General Account of the Public Treasury called "PDL 145T" will be opened by the Minister of Finance at the Central Bank of Congo, to ensure the availability of resources. Following the same instruction, the Minister of Finance shall open special accounts in local commercial banks for the benefit of the three Implementing Agencies provided for in the Programme and the National Coordination.

  - In accordance with each executing agency's disbursement plans approved by the Strategic Steering Committee (SPC), funds will be transferred directly to it by the Minister of Finance on the instruction of the Prime Minister.

# Communication & appropriation

- A communication and knowledge management strategy will be developed and implemented for transparency - accountability, sustainability of investments, information sharing between all actors and capitalization of experiences. UNDP recognizes the importance of ensuring the visibility of the Programme's achievements to enable stakeholders to assess the Government's efforts to promote the emergence of populations. In this respect, specific measures and initiatives will be taken to ensure communication on the Programme and social mobilization around its implementation, through the massive participation of beneficiary populations and all stakeholders.

# Cadre Legal

- This Programme Document  is the instrument defined in Article 1 of the Standard Basic Assistance Agreement ("SBAA") between the Government of [country] and UNDP, signed on [date]. All references in the SBAA to "Executing Organization" shall be deemed to refer to the "Implementing Partner".

- This project will be carried out by [name of organization] ("Implementing Partner") in accordance with its financial regulations, rules, practices and procedures, only to the extent that they do not contravene the principles of the UNDP Financial Regulations and Rules. Where the financial governance of an Implementing Partner does not include the necessary measures to ensure best value for money, equity, integrity, transparency and effective international competition, UNDP financial governance shall apply.

# Risk Management

- The PMU will monitor risks on a quarterly basis and communicate on the risk situation. Risks will be communicated as critical when impact is assessed at 5 and probabilities will be high. Management responses to critical risks will also be communicated in the  annual report.  The risks observed in the context of the programme, their probability ofoccurrence and the related mitigation measures are set out in the attached tablea:

| Table 3: Risks associated with PDL-145T |  |  |  |
| --- | --- | --- | --- |
| Risk | Probability | Impact | Mitigation measure |
| - Context risks |  |  |  |
| - The local context and the problemsrelated to the security situation | 4 | 4 | - Implementation of activities by local NGOs with flexible security requirements. - Implementation of certain activities by the Military Engineering (engineering structures, drilling, etc. if it has the material and human resources |
| - Lack of ownership of the programme by stakeholders | 4 | 3 | - Integration of communication and awareness-raising as a cross-cutting activity of the plan - Consider community actors and leaders as pillars of program implementation. - Accelerate and multiply awareness and information campaigns. - Ensuring the functioning of the CPTS |
| - Climate risks | 2 | 2 | - Conduct a comprehensive analysis of environmental and climate vulnerability |
| - Lack of trust between populations and state services, as well as program teams that may have a negative impact on project activities | 2 | 4 | - Initiate frameworks to improve the dialogue between authorities and populations and increase participation in accountability exercises and communication mechanisms, to rebuild trust (rapprochement between communities/populations and local state authorities) - Strengthen the CPTS and links with local development committees |
| - Programmatic risks |  |  |  |
| - Slow progress of the various stages of the program and purchases | 4 | 4 | - Set up a fast track disbursement procedure, and provide a team dedicated to financial and procurement operations. - The Programme Manager will hold regular meetings to anticipate the risks of constraints in the implementation of the programme and will take the necessary adjustment measures to accelerate the implementation |
| - Difficulty of access to certain very landlocked territories | 4 | 3 | - Permanent dialogue and proactivity of the Executing Agency with the Strategic Steering Committee, the National Operational Coordination and the CPTS |
| - Lack of national capacity to manage projects and work socio-economic infrastructure. | 3 | 4 | - Mobilize international expertisewith a preference to African expertise; - Use foreign service providers if necessary |
| - Institutional risks |  |  |  |
| - Non-ownership of the programme by provinces and local communities including communities | 2 | 2 | - Organize sharing and validation forums under the leadership of the Ministry of Planning jointly with the provinces and other Ministries involved in theprogram |
| - Occurrence of land& community conflicts | 4 | 4 | - Use customary arbitration for land issues; - Ask the state to give compensation if necessary. |
| - Low absorptive capacity of programme implementing partners (public, private or CSO) | 3 | 4 | - Capitalize on existing program project management frameworks for program implementation - Dedicate part of the resources to institutional and operational capacity building - Use partnership with effective CSOs, associations to increase the implementation capacities of agencies |
| - Fiduciary risks |  |  |  |
| - Corruption and poor governance of funds. | 3 | 4 | - Support the Government's efforts to coordinate and strengthen accountability in the management of funds for PDL - Using HACT as an approach to transferring funds while strengthening financial control and monitoring measures - Support the efforts of the Government and SCOs in the fight against corruption and strengthen financial accountability. |
| - Insufficient mobilization of national programme resources. | 3 | 4 | - Develop a resource mobilization strategy with bilateral and multilateral financial partners - Establish a realistic disbursement plan with the Ministry of Finance - Recourse to the supreme authority in case of total blockage |
| - Higher prices for inputs and equipment. | 3 | 4 | - Reprogramming component budgets to reflect them |

# ANNEXES

- SUMMARY OF THE BUDGET

| UNDP SYNTHESES |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Descriptions (Components) | Securities | Units | Total cost (in USD) | Average by territory |
| Estimated total cost of investment Local Development Programme of the 145 Territories |  |  |  | 619.829.499 |  |
|  | Component 1: Development of basic socio-economic infrastructure and services |  |  | 434.939.195 |  |
|  | Sub-Component 1.1: Development of basic socio-economic infrastructure |  |  | 282.417.194 |  |
|  | Rehabilitation of agricultural feeder roads | 3.721 | Km | 55.815.000 | 64 |
|  | Maintenance of agricultural feeder roads | 12.339 | Km | 30.847.500 | 210 |
|  | Structures | 84 | Number | 4.907.500 | 3 |
|  | Construction of a mini solar power plant | 172 | Mini Plants | 43.250.000 | 3 |
|  | Public lighting with solar system (1Km) | 6.720 | Floor lamp | 16 800 000 | 150 |
|  | Construction of a borehole of more or less 150 m with standpipe | 1.070 | Forage | 26 412 500 | 22 |
|  | Water source management | 266 | Number | 2 237 500 | 2 |
|  | Construction of modern steps with living space | 84 | Market | 29 817 194 | 2 |
|  | Construction of Administrative Buildings | 307 | Building | 18 330 000 | 5 |
|  | Construction of housing for the territory's management staff | 540 | Housing | 54 000 000 | 10 |
|  | Sub-Component 1.2: Improved access to basic social services |  |  | 152 522 001 |  |
|  | Health centre to be rehabilitated, built, equipped and completed | 283 | Health Centre (HC) | 58 620 000 | 5 |
|  | Health centers to be built and equipped | 242 | CS | 52 484 000 | 4 |
|  | Health centres to be completed and equipped | 1 |  | 150 000 |  |
|  | Health centres to be rehabilitated and equipped | 40 | CS | 5 986 000 | 1 |
|  | School to be rehabilitated, built and equipped | 423 | School | 93 902 000 | 8 |
|  | Schools to build and equip | 287 | School | 73 502 000 | 5 |
|  | Schools to be rehabilitated and equipped | 127 | School | 19 05 000 | 3 |
|  | Schools to be completed and equipped | 10 | School | 1 350 000 | 0 |
|  | Component 2: Value Chain Development |  |  | 108 000 000 |  |
|  | Structuring and professionalization of local producers by promising agricultural sectors in the 54 territories | 54 | Territory | 10 800 000 | 1 |
|  | Acquisition of 1296 production, processing and transport equipment for the 54 territories | 54 | Territory | 81 000 000 | 1 |
|  | Supply of 500,000 tonnes of inputs and seeds to local producers in the 54 territories | 54 | Territory | 16 200 000 | 1 |
|  |  |  |  | 663 756 390 |  |
| IV | Component 3: Local capacity-building |  |  | 4 940 000 |  |
| IV | Component 4: Geo-referenced system for monitoring and evaluation |  |  | 5 540 000 |  |
|  | TOTAL AMOUNT PROGRAMMATIC ACTIVITIES |  |  | 553 419 195 |  |
|  | Executing Agency (7% of Total Activities) |  |  | 38 739 344 |  |
|  | Contingencies (5% of Total Activities) |  |  | 27 670 960 |  |
|  | TOTAL GENERAL |  |  | 619 829 499 |  |

- Report on thequality assurance of the Programme

- Social and Environmental Screening Model

- Risk analysis

- Capacity assessment: Results of Implementing Partner capacity assessments (including HACT micro-evaluation)

- Terms of Reference of the Programme Steering Committee and Terms of Reference of Key Management Positions

- Program Management Unit Organization Chart

- Table of resource disbursements by the Government

- Mapping of implementing partners (UNDP subcontractors)

- Request for Approval or Delegation for Project Document that includes Construction Works

Note: Adjust signatures as needed

2  The Gender Marker measures how much a project invests in gender equality and women’s empowerment. Select one for each output: GEN3 (Gender equality as a principle objective); GEN2 (Gender equality as a significant objective); GEN1 (Limited contribution to gender equality); GEN0 (No contribution to gender quality)

Cassava cutters; cassava graters, grating cutters; mechanical press, diesel mill, retting tank (96m2), cassava peeler; Paddy rice husker, ; Winnower; peanut sheller; peanut oil press; diesel corn ginner etc.

Staff leading the territory designates: the Administrator of the Territory, the Administrator of the Territory - Political-Administrative Assistant, the Administrator of the Territory Assistant in charge of the Economy, Finance and Development, the Commander of the National Police, the Commander of the FARDC, the Head of Territorial Post of the ANR, the Head of Territorial Post of the DGM, the Agronomist of the Territory and for the Prosecutor,  as well as a house of passage.

The specialized services of the provincial administrations such as SENASEM, INERA, SNV and SENATRA, will be called upon to intervene in the programme and supervise operators and potential service providers. This will allow the implementation of the mechanism for sustaining the achievements of the program.

Average 5 per territory

UNDP publishes its project information (indicators, baselines, targets and results) to meet the International Aid Transparency Initiative (IATI) standards.  Make sure that indicators are S.M.A.R.T. (Specific, Measurable, Attainable, Relevant and Time-bound), provide accurate baselines and targets underpinned by reliable evidence and data, and avoid acronyms so that external audience clearly understand the results of the project.